## Milestones
Milestone | Scope | Planned | Status | Done | Total | % complete
M0 | Foundations | Sep 22-24 | Done | 23 | 23
M1 | Contracts | Sep 25-28 | Done | 28 | 28
M2 | Backend spine | Sep 29 - Oct 2 | Done (live on VPS) | 24 | 24
M3 | Agents + MCP | Oct 3-5 | Done | 15 | 15
M4 | Frontend | Oct 6-8 | Done (live on Vercel) | 13 | 13
M5 | Harden | Oct 9-11 | Backup video left (you) | 7 | 8
M6 | Submit | Oct 12-13 | In progress (video done) | 4 | 8
TOTAL

## Blockers
ID | What is blocked | Blocked by | Owner | Since | Severity | Notes
B6 | pnpm demo, M3 done-condition, chaos items, backup video | No model | User | Sep 23 | Done | Cleared Sep 29 with local Ollama (llama3 8B), no API quota. The first live runs found sixteen defects on the hire-to-settle path.
B7 | Interface visual verification | Chrome extension not connected | Claude | Sep 23 | Done | Rendered Sep 29 with headless Chrome. First render found the API sent no CORS headers, so every page said API unreachable; fixed.
B8 | Deploy + e2e against real hosting | Railway + Vercel accounts | User | Sep 22 | Done | Cleared Oct 7: backend on a Vultr VPS behind Caddy (https://api.64-177-41-175.sslip.io), site on Vercel (https://agentx-interface-iota.vercel.app); 16/16 deployment checks, three runs from the site settled. Railway not used (trial expired).
B10 | Verified source on the block explorer | EXPLORER_API_KEY is empty | User | Sep 28 | Open | Contracts are deployed but unverified, so an explorer link shows bytecode. The foundry.toml defect that also blocked this is fixed.
B11 | Repos readable by judges | Repos are private | User | - | Done | Public since Oct 6: agentx-contracts, agentx-backend, agentx-interface, agentx-docs (branch master).

## Tests
Repo | Suite | Tests | What it covers
agentx-contracts | AgentAccount | 38 | Caps, per-(target, selector) allowlist, forbidden approve-style selectors, session keys, two-step ownership, sweepNative
agentx-contracts | TaskEscrow | 31 | Job state machine, settlement, fee split, the permissionless exits
agentx-contracts | Guards | 25 | Reverts and boundary conditions
agentx-contracts | V2Findings | 23 | The Sep 30 audit findings, each failing on v1: SameOwner, dust, trapped payouts, dispute expiry, bounds, admin delay
agentx-contracts | V2Guards | 20 | Every new guard branch in v2
agentx-contracts | Adversarial | 15 | Hostile sequences against the escrow
agentx-contracts | StakeVault | 11 | Bonds per agent id, withdrawal delay, slashing to a recipient
agentx-contracts | Escrow.invariant | 9 | Solvency = locked + owed, fees, disputes, pause, mid-flight params
agentx-contracts | StakeVault.invariant | 4 | Vault balance always covers bonds
agentx-contracts | AgentAccount.invariant | 3 | No spend past a cap, no escape from the allowlist
agentx-contracts | MockUSDC | 5 | Test token
agentx-backend | signer | 38 | AgentAccount routing, caps, gas, replay, nonce release, the advisory lock released on one connection, named contract refusals, an HTTP 503 is retryable
agentx-backend | agent-core/orchestrator | 46 | Every failure branch, retrying a silent worker, a late accept waited for, never hiring itself, a model outage mid-selection; hire keys per run
agentx-backend | api | 38 | Registration, discovery, hiring, idempotent retries, the earned fast path, uuid public ids
agentx-backend | agent-core/worker | 43 | Offer loop, decline, transient accept, a failed submit retried without re-accepting
agentx-backend | sdk/client | 31 | Retries, idempotency keys, typed errors, NotAccepted
agentx-backend | agent-core/fallback | 26 | Provider chain (several Gemini models), cached replay and its pacing cap, recorders, no key in a URL
agentx-backend | api/x402 | 25 | Facilitator: settle, verify, redeem once, every forged receipt refused against the chain
agentx-backend | indexer/replay | 29 | Replay safety, v2 events, unresolved disputes earn nothing, reorgs, RPC blips are not reorgs, state only moves forward
agentx-backend | agent-core/injection | 23 | Untrusted-content containment; the judge's rating scale
agentx-backend | api/chaos | 23 | Malformed result, daily cap, result shape, on-chain hash
agentx-backend | db/constraints | 21 | Every documented database guarantee, tried by writing the bad row
agentx-backend | api/meta | 18 | Network and budget endpoints, v2 parameters, the 24h rollover
agentx-backend | mcp/tools | 17 | Tool descriptions, spend warnings, error retryability
agentx-backend | api/endpoints | 14 | Readiness, metrics, public-https endpoints, 404 on serial ids
agentx-backend | api/runs | 17 | Run lifecycle, durable trace, terminal state; the answer is written before `finished`; a per-orchestrator daily run cap
agentx-backend | signer/renewer | 6 | Renews the hosted accounts' 24 h session keys: only what is due, only accounts it owns, budgets kept
agentx-backend | agent-core/providers | 19 | Retries transient model errors; never a timeout or client error; JSON found in prose; a truncated reply moves the chain on
agentx-backend | signer/app | 11 | Validated /sign, RFC 7807, no internal message in a 500
agentx-backend | signer/keeper | 11 | Which exit is due at every deadline, including expireDispute
agentx-backend | service | 15 | Env validation, bearer compare, timeouts, shutdown, metrics, build metadata, token-gated /metrics
agentx-backend | api/status | 19 | Public /v1/status: states and numbers only, cached, bounded checks, indexer lag; a stopped indexer is down, an idle one is not
agentx-backend | indexer/progress | 2 | Head, indexed-block and lag gauges
agentx-backend | indexer/loop | 10 | Backoff, recovery, clean shutdown
agentx-backend | config/money | 8 | Base-unit formatting and parsing
agentx-backend | sdk/stream | 8 | SSE frames split at every byte offset
agentx-backend | agent-core/x402 | 7 | Paid endpoint: 402 quote, redeem before work
agentx-backend | api/hardening | 11 | Helmet, body limit, SSE cap, rate limit before auth (probes exempt); a database outage is 503 + retry-after; unknown ids 404
agentx-backend | api/coalesce | 3 | One health probe in flight, reused 5 s: a dead signer cannot starve DNS for the RPC
agentx-backend | api/identity | 6 | ERC-8004 id verified against the registry before it is stored
agentx-backend | api/submit | 6 | Signer token, timeout, an unreachable signer is a retryable outage
agentx-backend | mcp/server | 6 | A real MCP session: schemas, annotations, tool errors
agentx-backend | signer/auth | 6 | SIGNER_TOKEN, loopback-only without one
agentx-backend | api/cors | 6 | Cross-origin browser calls; credentials stay off
agentx-backend | api/auth | 4 | ax_<keyId>_<secret>, one indexed lookup, legacy keys
agentx-backend | api/skills | 4 | Per-skill reputation: a proven specialist ranks first for its skill even below a stronger generalist overall; counts what the indexer counts; every skill on the profile
agentx-backend | db/reputation | 3 | One shared score formula, identical to the indexer's for every history; no history scores 50; worker-fault reasons
agentx-backend | agent-core/model-failure | 5 | A used-up quota, a 429, overload and timeouts, a rejected key each named as such
agentx-backend | agent-core/recordings | 2 | Every committed model recording is still reachable from the current prompts, so the cached demo cannot silently break
agentx-backend | agent-core/judge | 1 | The judge rates a step against its own subtask, not the whole goal
agentx-interface | lib/api + subscribe | 19 | formatUnits past 2^53; SSE kinds, bad frames; only a terminal event ends a run; reconnect + replay reset; 5xx/503 read as sentences
agentx-interface | lib/search | 22 | Docs search: typos, stems, synonyms, identifiers, AND, ranking, hostile input, sections from HTML
agentx-interface | lib/links | 9 | Explorer links: https + known host only; uuid and agent id parsing
agentx-interface | components | 12 | RunTrace (hostile links, money, live region), NetworkBadge (never assumes testnet)
agentx-interface | lib/wallet | 6 | Addresses and RPC validated before the wallet is asked; chain added on 4902
agentx-interface | lib/agent-card | 4 | ERC-8004 registration-v1 card and its data: URI, non-ASCII safe
agentx-interface | lib/format | 5 | Relative time and durations, refusing nonsense input
agentx-interface | lib/review | 6 | The on-chain review under a settled step: links the settlement transaction, says so when the registry refused, claims nothing before indexing or for a refund
agentx-interface | components/StepList | 4 | Every step status as a label with its reason, never a code
TOTAL

## Defects
Severity | Defect | How it was caught | Status
Critical | Every escrow job would have been disputed: the API stored the delivery envelope as the result, so good work failed the required-field check | Auditing docs against the routes | Fixed
Critical | An indexer restart could manufacture reputation: the bump was not idempotent while replays are routine | Chaos item 2 | Fixed
Critical | The on-chain commitment was the spec hash, not the result hash, so T4's claim was false | The same docs audit | Fixed
Critical | Fee-on-transfer tokens left the escrow insolvent; the balance-delta guard was documented but absent | Adversarial review | Fixed
High | A failed broadcast burned the idempotency key forever; topping up the wallet did not help | Chaos item 7 | Fixed
High | A malformed result was stored and signed for, despite a comment claiming it was validated | Chaos item 4 | Fixed
High | Session keys had no lifetime bound, though the threat model claimed 24h | Security pass T1-T17 | Fixed
High | The API sent database ids to the contract, so a worker received nothing while every status code said success | Live-chain e2e | Fixed
Medium | Run marked done before its terminal event was recorded; a reader could get a trace missing its ending | A flaky test, diagnosed | Fixed
Medium | The indexer retried a failing RPC every 2s forever, a retry storm against a rate limiter | Chaos item 5 | Fixed
Medium | make coverage and the CI coverage step failed every time: forge coverage disables viaIR, which this project needs | Deep testing pass | Fixed
Medium | Nothing tested AgentAccount access control; removing onlyOwner would have failed no test | Coverage report | Fixed
Medium | The live-chain verifier reported success while failing, and used a constant specHash that matched an older run | Full recheck | Fixed
Medium | The secret scanner fired on ordinary English, training everyone to bypass the hook that guards real keys | Writing a README | Fixed
Low | T15 claimed an SSRF guard for a fetch that does not exist anywhere | Security pass | Documented
Low | REDIS_URL and API_JWT_SECRET pointed at mechanisms with no implementation | docs/08 audit | Removed
Critical | No demo job had ever settled: eight defects between hire and settlement, each hiding the next | First live runs, Sep 29 | Fixed
Critical | Spending caps were enforced nowhere for EOA agents (all of them); the signer read AgentAccount, failed, and allowed | Docs audit, Sep 29 | Fixed
Critical | No process ever sent the escrow's permissionless exits; stranded money stayed stranded | Docs audit, Sep 29 | Fixed: keeper
Critical | A retried hire inserted a phantom job each time, backed by no transaction | Live e2e, Sep 29 | Fixed
Critical | The indexer linked jobs by spec hash alone, crediting a worker for an old run's payment | Live e2e, Sep 29 | Fixed
High | Every refund, including a client's cancel, counted as the worker failing | Docs audit, Sep 29 | Fixed
High | Agents registered through the API or /register could never be hired: nothing set chain_agent_id | Docs audit, Sep 29 | Fixed
High | The API sent no CORS headers; every browser request was refused | First browser render, Sep 29 | Fixed
High | fastPathMinScore was read by nothing; unproven workers were paid up front | Docs audit, Sep 29 | Fixed
High | The signer accepted signing requests from anyone who could reach it | Docs audit, Sep 29 | Fixed: token
High | The judge's 0-100 score came back on three scales; approved work was disputed | Live runs, Sep 29 | Fixed
Medium | Recorders sharing a cache file erased each other; a replay lost two of three steps | Cached replay, Sep 29 | Fixed
Medium | A worker abandoned a job the API had told it to retry | Mid-job chaos run, Sep 29 | Fixed
Medium | pnpm demo passed with one step of three settled | Cached replay, Sep 29 | Fixed
Medium | /v1/budget ignored the 24h rollover | Docs audit, Sep 29 | Fixed
Medium | Deploy ignored ARBITER_ADDRESS and FEE_RECIPIENT; make drift called a script that did not exist | Docs audit, Sep 29 | Fixed
High | After a reorg a re-mined settlement was credited twice and a dropped one kept forever | Reorg review, Sep 29 | Fixed: dedupe + halt
High | No agent used AgentAccount, so the on-chain cap claim held for nothing | Docs audit, Sep 29 | Fixed: orchestrator
Medium | A failed broadcast's nonce claim blocked every later request as in flight | AgentAccount live run | Fixed
Medium | An empty gas wallet was reported as an unreachable RPC (503 matched inside tx hex) | AgentAccount live run | Fixed
Low | A disputed job had no timeout; only the arbiter could resolve it | Docs audit, Sep 29 | Fixed in v2: expireDispute
Critical | The signer's per-agent advisory lock could stay held forever (taken and released on different pooled connections) | Session 26 audit; reproduced in a test | Fixed
Critical | API auth ran scrypt against every stored key on every request: 12.9 s per request at a few hundred keys | Session 26 audit | Fixed: keyId + SHA-256
Critical | Reputation farming by self-hire; a payout to a bad wallet trapped the job | Contract audit, Sep 30 | Fixed in v2
High | Jobs and runs were enumerable by serial id | Session 26 audit | Fixed: uuid public ids
High | A worker abandoned finished work when a submit failed transiently | Slow-RPC chaos run on v2 | Fixed
High | Explorer links from the API went straight into href (a javascript: URL would run) | Interface audit, Sep 30 | Fixed: allowlist
High | The indexer walked a job state backwards; a delivered job read accepted and approve was refused | M5-06 timed runs, Session 27 | Fixed: forward-only projection
High | A Railway build could not have built: chain facts came from a sibling checkout | Deploy rehearsal, Session 27 | Fixed: chain/ + drift check
High | An HTTP 503 from the RPC was reported INVALID_STATE, so workers gave up accepts and finished submits | 20%-lossy chaos run, Session 27 | Fixed
High | A late accept made the cancel fail and the orchestrator abandoned the delivery | 20%-lossy chaos run, Session 27 | Fixed
Medium | An unreachable signer was reported as INSUFFICIENT_FUNDS | Session 26 audit | Fixed
Medium | The indexer halted on one RPC 503 as if for a reorg | Session 26 audit | Fixed
Medium | SSE sent no headers until the first 25 s heartbeat | Test written for the audit | Fixed
Medium | The demo registered workers' records under the wrong owner once they owned their identities | First live v2 run | Fixed
High | The orchestrator offered its own capability to the planner and tried to hire itself | Mid-job chaos run, Sep 30 | Fixed
High | A model outage while choosing an agent aborted the whole run instead of ending the step | Gemini live run, Sep 30 | Fixed
Medium | Why a plan failed was discarded; every cause read as 'could not reach a model' | Gemini live run, Sep 30 | Fixed
Medium | The default Gemini model was retired (404); Session 23's Gemini failures were likely this | Gemini live run, Sep 30 | Fixed: gemini-3.8-flash
Medium | The Gemini key travelled in the URL query string | Gemini live run, Sep 30 | Fixed: header
Medium | The demo reused a CREATE2 salt after an aborted run; createAccount reverted | Live run, Sep 30 | Fixed
Medium | The demo harness did not survive a dropped broadcast; one injected 503 aborted it | Slow-RPC chaos, Sep 30 | Fixed: resend signed bytes
Low | The live run page would never have shown a plan-failed event (no SSE listener) | Review, Sep 30 | Fixed

## Outstanding
Area | Item | Owner | Priority | Notes
Contracts | Verify source on the explorer | User | P1 | Needs EXPLORER_API_KEY; the config defect is fixed.
Submit | Fill the portal and submit | User | P0 | Field-by-field text in docs/18-portal-entry.md; the judges' orchestrator key goes in the private field only.
Hosting | Destroy the VPS after judging | User | P2 | It bills monthly once the credit ends. Daily database backups run on it (03:00 UTC, 7 kept).
Testnet | Testnet MON for hosted runs | User | P1 | A hosted run measured 0.21 MON; a local demo run ~0.5 MON. See PROGRESS for current balances; seed-hosted.mjs --top-up refills the hosted agents.
Post-hack | ERC-8183 conformance: new kernel + AGENTX evaluator + hook | Claude | P4 | Mapping written: docs/12. Needs a redeploy, so after the deadline.

## About
Field | Value
Generated by | docs/build-status-workbook.py — rebuild rather than edit by hand
Source of truth | agentx-backend/PROGRESS.md
As of | 2026-10-08
Deadline | 2026-10-13, 11:59 PM ET
Track | 4 — Trust, Identity & AI Infrastructure
Live network | Monad testnet, chain 10143
TaskEscrow (v2) | 0x4feED0338761817417Fd1dDdFC8331D16AEB370D
Live site | https://agentx-interface-iota.vercel.app (Vercel, deploys from master)
Live API | https://api.64-177-41-175.sslip.io (Vultr VPS behind Caddy; daily database backup)
Tests | 862 unit/integration (184 contracts, 591 backend, 87 interface) + 72 browser tests on 5 engines (360 runs)
Repos | agentx-contracts, agentx-backend, agentx-interface, agentx-docs — public, branch master
Formulas | Totals and percentages are formulas so the sheet recalculates when a count changes. They were NOT recalculated when written — that needs LibreOffice, which the build machine lacks — so Excel computes them on first open.